## Taul1
NAME | DATE | TIME | TASK
Joel | 2018-12-03 | 9.00 - 15.00 | Learned github again, created a repository (and tested it), brainstormed on a notebook and started to work on the number conversion stuff.
Oscar | 2018-12-03 | 9.00 - 19.00 | Learned github again, created a repository (and tested it), brainstormed on a notebook and worked on Random Value function.
Joel | 2018-12-04 | 9.00 - 15.00 | Started to work on HTML, CSS Design/Function and a tab changer.
Oscar | 2018-12-04 | 9.00 - 18.00 | Fixing the "Random Value function" so it works better and trying to fix some bugs
Oscar | 2018-12-05 | 8.30 - 15.00 | Still trying to make the Random Value function work. Added the Number System with a button. But it does not work right now
Joel | 2018-12-06 | 13.00 - 15.00 | Started working on the combinatorics: made a selector and a base for the permutations. Had a fever so I couldn't come to school yesterday.
Oscar | 2018-12-07 | 9.00 - 14.30 | Found a solution for the Random Value function and now it should be ok. One thing needs to be fix and its remove or add the 0 into the function. Continued working on the Number System but the button I made does not work at all.
Joel | 2018-12-07 | 9.00 - 14.30 | Continued the work on the combinatorics (made the permutations without replacement work).
Oscar | 2018-12-08 | 8.00 - 15.00 | I fixed the button problem and added a table with values from 0-50. So the button now hides the information.
Joel | 2018-12-10 | 9.00 - 14.00 | Finished the combinatorics, fixed some minor bugs in the number converter that alerted the user at wrong occasions and did some css styling.
Oscar | 2018-12-10 | 8.30 - 15.00 | Trying to solve the Truth Table and small bug fix.
Joel | 2018-12-11 | 9.00 - 14.00 | Started working on a "number checker", fixed more bugs and did some more styling on the css.
Oscar | 2018-12-11 | 9.10 - 18.00 | Almost done with the Truth Table and did some cleaning of the code. Added a logo to our project and a few style things in HTML/CSS.
Joel | 2018-12-12 | 13.00 - 15.30 | (Our work was interrupted in the morning because of an exam in JavaScript by Kari Laitinen and a swedish exam) Finished the number checker, merged both working branches into the master branch and fixed the problems that came with the merging.
Oscar | 2018-12-12 | 13.00 - 16.00 | (Our work was interrupted in the morning because of an exam in JavaScript by Kari Laitinen) Fixed a few bugs with the Random Value function and the Truth Table.
Joel | 2018-12-13 | 9.00 - 12.00 | Fixed a few things in the HTML code and started the project report. Went home early due to a headache and continued with the report later in the evening (18.00 - 23.00).
Oscar | 2018-12-13 | 8.30 - 18.00 | Truth Table works now and showing the right values. Ive been fixing the last things with the style of the website. The project is almost completely done. Joel and I started with the project report.
Joel | 2018-12-14 | 9.00 - 15.00 | Finished the project report and fixed some bugs related to Infinity and NaN in the combinatorics.
Oscar | 2018-12-14 | 9.00 - 15.00 | Finished the project report with Joel and looking through the website one more time to see if we missed something.